MATRIX TSL · UK SALES

Scotland Sales Tour 2026

Visit planning, Monday 1 to Friday 5 June 2026

| Lead | Alfie Dobson (UK Sales Manager) |
| --- | --- |
| Base | Halifax, West Yorkshire |
| Dates | Monday 1 June to Friday 5 June 2026 (five working days) |
| Target sector | UK colleges and universities, engineering departments |
| Products | Locktronics, Three Phase, Electrical Machines (EM), Industrial Maintenance (IM), Structures, Pneumatics, FM |
| Visit model | Up to 3 visits per day. 1 hour for a standard demo, 2 hours for a broader product range. |
| Vehicle | Jumbo van from Shire Link, Huddersfield. £431.25 for the week ex VAT, insurance included. |
| Options | Route A: Scotland only, up and back via M6/M74. Route B: Scotland with a North East return via Newcastle and Teesside. |

## 1. Trip objectives

The plan is to hit as many Scottish college and university engineering departments as we can fit into one week, show the core Matrix TSL kit, and build the relationships we'll need for the 2026/27 academic year.

Two route options are below. The right one depends on how many visits we can firm up by mid May, and whether we commit to the bigger van.

## 2. Products to demo

One van load, same kit at every stop. How much we actually show on the day depends on what courses they run and how much time they give us.

- Locktronics (electrical installation trainer)

- Three Phase

- Electrical Machines (EM)

- Industrial Maintenance (IM)

- Structures

- Pneumatics

- FM

If we go for the bigger van we can take the extended kit as well:

- Wind Tunnel

- All 3 × IM products

- Fluids

- Flowcode or E-blocks demo rig (suggestion, confirm with engineering)

## 3. Visit model and driving

- Three demo visits a day is realistic, as long as total driving stays under about two hours

- Standard visit is one hour, for colleges with a narrower course range

- Longer visit is two hours, for the bigger departments where there's more to show

- First visit between 8:30 and 9:00, finish by 5pm

- Independent schools and sixth forms in the source list aren't a great fit for this kit, so they're not on the schedule

## 4. Van hire

Booked with Shire Link in Huddersfield Shire Link are on Halifax Rd, Huddersfield (HD3 3BS), about 10 minutes from home. The Jumbo van is an extra long wheelbase Ford Transit with insurance included in the price. £431.25 for the week ex VAT (£517.50 inc VAT). 15.1 cubic metres of loadspace, 4.26 m long, 2.03 m high inside, 1,195 kg payload. Plenty of room for the full kit including the wind tunnel. £300 deposit on collection. Pickup Friday afternoon after 3pm so we can load up and leave Halifax first thing Monday morning. Phone 01484 427701 to confirm the booking.

# Route A: Scotland only

Up the M6 and M74, and back the same way. This route reaches Stirling, Perth, Dundee, St Andrews and Fife, so it's the right choice if most of the interest sits in central and eastern Scotland.

Route A summary 13 visits across five days, roughly 900 miles end to end. Overnights: Glasgow twice, then Dundee, then Edinburgh, then home. Day 1 is a half day of driving, arriving in Dumfries at about 10:30. Day 2 in Glasgow is a lighter driving day so any overrun from Day 1 or 2 can be absorbed without shifting the rest of the week.

## Route A overview

| Day | Date | Leg | Visits planned | Overnight |
| --- | --- | --- | --- | --- |
| Day 1 | Mon 1 Jun | Halifax to Glasgow | Drive up (AM), Dumfries and Galloway College, South Lanarkshire College | Glasgow |
| Day 2 | Tue 2 Jun | Glasgow cluster | University of Strathclyde, City of Glasgow College, Glasgow Caledonian | Glasgow |
| Day 3 | Wed 3 Jun | Glasgow to Dundee | University of Stirling, Perth College UHI, University of Dundee | Dundee |
| Day 4 | Thu 4 Jun | Dundee to Edinburgh | Dundee and Angus College, University of St Andrews, Fife College | Edinburgh |
| Day 5 | Fri 5 Jun | Edinburgh to Halifax | Heriot-Watt University, Edinburgh College, drive home | Home |

## Route A daily schedule

### Day 1, Monday 1 June: Halifax to Glasgow (morning drive, afternoon visits)

| Time | Activity | Duration | Type |
| --- | --- | --- | --- |
| 07:00 | Depart Halifax (loaded van) |  | Drive |
| 10:30 | Arrive Dumfries (M62, M6, M74, about 180 mi) | 3 h 30 | Drive |
| 11:00 | Dumfries and Galloway College | 1 h | Visit |
| 12:15 | Drive to East Kilbride (M74 north) | 1 h 30 | Drive |
| 13:45 | South Lanarkshire College (East Kilbride) | 1 h | Visit |
| 15:00 | Drive into Glasgow, check in hotel | 30 m | Overnight |

### Day 2, Tuesday 2 June: Glasgow cluster (lighter driving day)

| Time | Activity | Duration | Type |
| --- | --- | --- | --- |
| 09:00 | University of Strathclyde | 2 h | Visit |
| 11:15 | Short drive across city centre | 15 m | Drive |
| 11:30 | City of Glasgow College | 1 h | Visit |
| 13:30 | Glasgow Caledonian University | 2 h | Visit |
| 15:45 | Return to hotel, admin time |  | Overnight |

### Day 3, Wednesday 3 June: Glasgow to Stirling to Perth to Dundee

| Time | Activity | Duration | Type |
| --- | --- | --- | --- |
| 08:30 | Drive Glasgow to Stirling (M80) | 45 m | Drive |
| 09:30 | University of Stirling | 2 h | Visit |
| 11:45 | Drive to Perth (A9) | 45 m | Drive |
| 12:30 | Perth College UHI | 1 h 30 | Visit |
| 14:15 | Drive to Dundee | 30 m | Drive |
| 14:45 | University of Dundee | 1 h 30 | Visit |
| 16:30 | Check in, Dundee hotel |  | Overnight |

### Day 4, Thursday 4 June: Dundee to St Andrews to Fife to Edinburgh

| Time | Activity | Duration | Type |
| --- | --- | --- | --- |
| 09:00 | Dundee and Angus College | 1 h | Visit |
| 10:15 | Drive to St Andrews | 30 m | Drive |
| 10:45 | University of St Andrews | 2 h | Visit |
| 13:00 | Drive to Dunfermline (A91, M90) | 1 h 15 | Drive |
| 14:15 | Fife College (Dunfermline) | 1 h | Visit |
| 15:30 | Drive to Edinburgh (Forth Road Bridge) | 45 m | Overnight |

### Day 5, Friday 5 June: Edinburgh to Halifax

| Time | Activity | Duration | Type |
| --- | --- | --- | --- |
| 08:30 | Drive to Heriot-Watt campus (Riccarton) | 30 m | Drive |
| 09:00 | Heriot-Watt University | 2 h | Visit |
| 11:15 | Drive across Edinburgh | 30 m | Drive |
| 11:45 | Edinburgh College (Sighthill) | 1 h | Visit |
| 12:45 | Drive home via M74 and M6 | 4 h | Drive |
| 16:45 | Arrive Halifax |  | Overnight |

# Route B: Scotland with a North East return

Same drive up to Glasgow as Route A, but coming back down through Edinburgh, Newcastle, Durham and Teesside rather than pushing further into central Scotland. We lose Stirling, Perth, Dundee, St Andrews and Fife, but pick up the Tyneside and Teesside cluster on the way home.

Route B summary 14 visits across five days plus one optional, roughly 850 miles end to end. Overnights: Glasgow twice, then Edinburgh, then Newcastle, then home. Worth it if we can get enough customers down the North East corridor to book visits. Over 30 institutions sit along that return leg. St Andrews, Fife and the central Scotland corridor are the big trade off. Those can go in a separate trip later.

## Route B overview

| Day | Date | Leg | Visits planned | Overnight |
| --- | --- | --- | --- | --- |
| Day 1 | Mon 1 Jun | Halifax to Glasgow | Drive up (AM), Dumfries and Galloway College, South Lanarkshire College | Glasgow |
| Day 2 | Tue 2 Jun | Glasgow cluster | University of Strathclyde, Glasgow Caledonian, University of Glasgow | Glasgow |
| Day 3 | Wed 3 Jun | Glasgow to Edinburgh | City of Glasgow College, West Lothian College, University of Edinburgh | Edinburgh |
| Day 4 | Thu 4 Jun | Edinburgh to Newcastle | Heriot-Watt, Edinburgh College, Northumbria University | Newcastle |
| Day 5 | Fri 5 Jun | Newcastle to Halifax | Newcastle College, Gateshead College, Durham University | Home |

## Route B daily schedule

### Day 1, Monday 1 June: Halifax to Glasgow (morning drive, afternoon visits)

| Time | Activity | Duration | Type |
| --- | --- | --- | --- |
| 07:00 | Depart Halifax (loaded van) |  | Drive |
| 10:30 | Arrive Dumfries (M62, M6, M74, about 180 mi) | 3 h 30 | Drive |
| 11:00 | Dumfries and Galloway College | 1 h | Visit |
| 12:15 | Drive to East Kilbride (M74 north) | 1 h 30 | Drive |
| 13:45 | South Lanarkshire College (East Kilbride) | 1 h | Visit |
| 15:00 | Drive into Glasgow, check in hotel | 30 m | Overnight |

### Day 2, Tuesday 2 June: Glasgow cluster

| Time | Activity | Duration | Type |
| --- | --- | --- | --- |
| 09:00 | University of Strathclyde | 2 h | Visit |
| 11:30 | Glasgow Caledonian University | 1 h | Visit |
| 13:00 | Short drive to West End | 30 m | Drive |
| 13:30 | University of Glasgow | 2 h | Visit |
| 15:45 | Return to hotel, admin time |  | Overnight |

### Day 3, Wednesday 3 June: Glasgow to Edinburgh (via Livingston)

| Time | Activity | Duration | Type |
| --- | --- | --- | --- |
| 09:00 | City of Glasgow College | 1 h | Visit |
| 10:15 | Drive to Livingston (M8) | 40 m | Drive |
| 11:00 | West Lothian College | 1 h 30 | Visit |
| 13:00 | Drive to Edinburgh (M8) | 30 m | Drive |
| 13:45 | University of Edinburgh | 2 h | Visit |
| 16:00 | Check in, Edinburgh hotel |  | Overnight |

### Day 4, Thursday 4 June: Edinburgh to Newcastle

| Time | Activity | Duration | Type |
| --- | --- | --- | --- |
| 09:00 | Heriot-Watt University | 2 h | Visit |
| 11:30 | Drive across Edinburgh | 30 m | Drive |
| 12:00 | Edinburgh College (Sighthill) | 1 h 30 | Visit |
| 13:45 | Drive south A1 and A68 to Newcastle | 2 h 15 | Drive |
| 16:00 | Northumbria University | 1 h 30 | Visit |
| 17:45 | Check in, Newcastle hotel |  | Overnight |

### Day 5, Friday 5 June: Newcastle to Halifax (via Durham)

| Time | Activity | Duration | Type |
| --- | --- | --- | --- |
| 09:00 | Newcastle College | 1 h | Visit |
| 10:30 | Short drive to Gateshead | 20 m | Drive |
| 10:50 | Gateshead College | 1 h | Visit |
| 12:10 | Drive to Durham | 30 m | Drive |
| 12:45 | Durham University | 2 h | Visit |
| 14:45 | Drive home via A1(M) and M1 | 2 h 15 | Drive |
| 17:00 | Optional: Darlington College en route | 1 h | Visit |

# College reference, by geographic cluster

Every institution from the source list, grouped by region. Distance is miles off the natural driving route. This is the long list for firming up customer appointments before we lock in a route.

## Scotland bound corridor (common to both routes)

### Yorkshire and Lancashire (outbound warm up)

| Institution | Type | Location | Miles off route |
| --- | --- | --- | --- |
| Burnley College | College | Burnley | 13 mi |
| NCC, Nelson and Colne College | College | Nelson | 10 mi |
| Craven College | College | Skipton | 0 mi |
| The Aviation Academy (Craven College) | College | Skipton | 0 mi |
| Lancaster University | University | Bailrigg | 15 mi |
| Lancaster and Morecambe College | College | Morecambe | 14 mi |

### Cumbria

| Institution | Type | Location | Miles off route |
| --- | --- | --- | --- |
| Kendal College | College | Kendal | 5 mi |
| Ullswater Community College | College | Penrith | 1 mi |
| University of Cumbria | University | Carlisle | 0 mi |
| Carlisle College | College | Carlisle | 0 mi |

### Dumfries and Galloway (border crossing)

| Institution | Type | Location | Miles off route |
| --- | --- | --- | --- |
| Dumfries and Galloway College | College | Dumfries | 10 mi |
| Scotland's Rural College (SRUC) Barony | College | Dumfries | 5 mi |

### Greater Glasgow (dense cluster)

| Institution | Type | Location | Miles off route |
| --- | --- | --- | --- |
| Hamilton College | College | Hamilton | 1 mi |
| South Lanarkshire College | College | East Kilbride | 5 mi |
| New College Lanarkshire | College | Motherwell | 1 mi |
| City of Glasgow College | College | Glasgow | 0 mi |
| University of Strathclyde | University | Glasgow | 0 mi |
| University of Glasgow | University | Glasgow | 2 mi |
| Glasgow Caledonian University | University | Glasgow | 0 mi |
| Glasgow Kelvin College | College | Glasgow | 1 mi |
| Glasgow Clyde College (main) | College | Glasgow | 2 mi |
| Glasgow Clyde College (Cardonald) | College | Glasgow | 4 mi |
| Glasgow Clyde College (Anniesland) | College | Glasgow | 3 mi |
| University of the West of Scotland | University | Paisley | 7 mi |
| West College Scotland | College | Clydebank | 6 mi |

### Central Scotland (Forth Valley)

| Institution | Type | Location | Miles off route |
| --- | --- | --- | --- |
| Forth Valley College | College | Falkirk | 6 mi |
| University of Stirling | University | Stirling | 2 mi |

### Perth and Dundee

| Institution | Type | Location | Miles off route |
| --- | --- | --- | --- |
| Glenalmond College | College | Perth | 6 mi |
| Perth College UHI | College | Crieff Road | 1 mi |
| University of Dundee | University | Dundee | 0 mi |
| Dundee and Angus College | College | Dundee | 2 mi |
| University of Abertay | University | Dundee | 0 mi |

### Fife and St Andrews

| Institution | Type | Location | Miles off route |
| --- | --- | --- | --- |
| Madras College | School | St Andrews | 8 mi |
| University of St Andrews | University | St Andrews | 8 mi |
| Fife College | College | Dunfermline | 0 mi |

### Edinburgh and the Lothians

| Institution | Type | Location | Miles off route |
| --- | --- | --- | --- |
| West Lothian College | College | Livingston | 8 mi |
| Heriot-Watt University | University | Edinburgh | 4 mi |
| Edinburgh Napier University | University | Edinburgh | 3 mi |
| Edinburgh College | College | Edinburgh | 1 mi |
| University of Edinburgh | University | Edinburgh | 0 mi |
| Stewart's Melville College | Ind. school | Edinburgh | 0 mi |
| George Watson's College | Ind. school | Edinburgh | 2 mi |

## North East England (Route B only)

These clusters only come into play if we go with Route B. Kept here for completeness in case we pull enough customer interest to justify the detour, or to use as a starting point for a separate North East trip later in the year.

### Northumberland and Tyneside (Route B only)

| Institution | Type | Location | Miles off route |
| --- | --- | --- | --- |
| Northumberland College | College | Ashington | 5 mi |
| Seaton Burn College | College | Newcastle | 1 mi |
| Newcastle University | University | Newcastle | 0 mi |
| Northumbria University | University | Newcastle | 0 mi |
| Newcastle College | College | Newcastle | 0 mi |
| Tyne Metropolitan College | College | Wallsend | 5 mi |
| Tyne Coast College | College | South Shields | 8 mi |
| South Tyneside College | College | South Shields | 8 mi |
| Gateshead College | College | Gateshead | 1 mi |
| Emmanuel College | College | Gateshead | 0 mi |
| Derwentside College | College | Consett | 10 mi |
| St Wilfrid's RC College | College | Tyne and Wear | 7 mi |
| NA College | College | Washington | 2 mi |

### Wearside, Durham and Tees (Route B only)

| Institution | Type | Location | Miles off route |
| --- | --- | --- | --- |
| University of Sunderland | University | Sunderland | 7 mi |
| Sunderland College | College | Sunderland | 6 mi |
| Southmoor Academy (Sixth Form) | Sixth form | Sunderland | 7 mi |
| Durham University | University | Durham | 2 mi |
| New College Durham | College | Durham | 3 mi |
| The Studio Sixth Form | Sixth form | Durham | 4 mi |
| East Durham College | College | Peterlee | 7 mi |
| Bishop Auckland College | College | Bishop Auckland | 7 mi |
| Hartlepool College of FE | College | Hartlepool | 12 mi |
| Hartlepool Sixth Form | Sixth form | Hartlepool | 11 mi |
| Bede Sixth Form College | College | Billingham | 9 mi |
| Teesside University | University | Middlesbrough | 12 mi |
| Middlesbrough College | College | Middlesbrough | 12 mi |
| Trinity Catholic College | College | Middlesbrough | 13 mi |
| Stockton Sixth Form College | College | Stockton | 8 mi |
| Stockton Riverside College | College | Thornaby | 10 mi |
| St John's School and Sixth Form | Sixth form | Bishop Auckland | 7 mi |
| Darlington College | College | Darlington | 3 mi |

# Decision points and next steps

## Which route?

- Route A if most of the interest is Scottish, especially Dundee, Perth or Stirling contacts

- Route B if we can get Tyneside or Teesside customers to confirm visits, more institutions per mile on the return leg

- If we fill 18 or more visits, Route B soaks them up better because there's more to hit on the way home

## Actions this week

- Confirm the Shire Link booking on 01484 427701, pickup Friday afternoon after 3pm

- Email target list for soft appointment requests (send week of 11 May)

- Book four hotels once the route is locked in. Route A: Glasgow twice, Dundee, Edinburgh. Route B: Glasgow twice, Edinburgh, Newcastle.

- Prep the demo kit checklist against the product list in Section 2 and plan the van load

- Draft a one page handout per product line to leave with each contact

## Actions week of 25 May

- Confirm appointments by phone five working days out

- Print the itinerary, load it into the sat nav, and finalise van collection

- Email courtesy reminders to everyone who's confirmed

Prepared by Alfie Dobson, Matrix TSL UK Sales, April 2026